{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1 (2)","Sheet2","Sheet3"],"not_rendered":{"external_links":1,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1 (2)","index":0,"n_rows":31,"n_cols":28,"rows_kept":31,"merged":[[0,0,0,27],[2,0,2,27],[3,0,6,0],[3,1,6,1],[3,2,6,2],[3,3,6,3],[3,4,3,5],[3,6,6,6],[3,7,6,7],[3,8,3,9],[3,10,6,10],[3,11,3,13],[3,14,6,14],[3,15,6,15],[3,16,6,16],[3,17,6,17],[3,18,6,18],[3,19,6,19],[3,20,6,20],[3,21,3,26],[3,27,6,27],[4,4,6,4],[4,5,6,5],[4,8,6,8],[4,9,6,9],[4,11,6,11],[4,12,6,12],[4,13,6,13],[4,21,6,21],[4,22,4,25],[4,26,6,26],[5,22,5,23],[5,24,5,25],[7,0,9,0],[7,1,9,1],[7,2,9,2],[7,3,9,3],[7,4,9,4],[7,5,9,5],[7,6,9,6],[7,7,9,7],[7,8,9,8],[7,9,9,9],[7,10,9,10],[7,14,9,14],[7,15,9,15],[7,16,9,16],[7,17,9,17],[7,18,9,18],[7,19,9,19],[7,20,9,20],[7,21,9,21],[7,22,9,22],[7,23,9,23],[7,24,9,24],[7,25,9,25],[7,26,9,26],[7,27,9,27],[10,0,12,0],[10,1,12,1],[10,2,12,2],[10,3,12,3],[10,4,12,4],[10,5,12,5],[10,6,12,6],[10,7,12,7],[10,8,12,8],[10,9,12,9],[10,10,12,10],[10,14,12,14],[10,15,12,15],[10,16,12,16],[10,17,12,17],[10,18,12,18],[10,19,12,19],[10,20,12,20],[10,21,12,21],[10,22,12,22],[10,23,12,23],[10,24,12,24],[10,25,12,25],[10,26,12,26],[10,27,12,27],[13,0,15,0],[13,1,15,1],[13,2,15,2],[13,3,15,3],[13,4,15,4],[13,5,15,5],[13,6,15,6],[13,7,15,7],[13,8,15,8],[13,9,15,9],[13,10,15,10],[13,14,15,14],[13,15,15,15],[13,16,15,16],[13,17,15,17],[13,18,15,18],[13,19,15,19],[13,20,15,20],[13,21,15,21],[13,22,15,22],[13,23,15,23],[13,24,15,24],[13,25,15,25],[13,26,15,26],[13,27,15,27],[16,0,17,0],[16,1,17,1],[16,2,17,2],[16,3,17,3],[16,4,17,4],[16,5,17,5],[16,6,17,6],[16,7,17,7],[16,8,17,8],[16,9,17,9],[16,10,17,10],[16,14,17,14],[16,15,17,15],[16,16,17,16],[16,17,17,17],[16,18,17,18],[16,19,17,19],[16,20,17,20],[16,21,17,21],[16,22,17,22],[16,23,17,23],[16,24,17,24],[16,25,17,25],[16,26,17,26],[16,27,17,27],[18,0,19,0],[18,1,19,1],[18,2,19,2],[18,3,19,3],[18,4,19,4],[18,5,19,5],[18,6,19,6],[18,7,19,7],[18,8,19,8],[18,9,19,9],[18,10,19,10],[18,14,19,14],[18,15,19,15],[18,16,19,16],[18,17,19,17],[18,18,19,18],[18,19,19,19],[18,20,19,20],[18,21,19,21],[18,22,19,22],[18,23,19,23],[18,24,19,24],[18,25,19,25],[18,26,19,26],[18,27,19,27],[23,0,23,27],[24,0,24,27],[25,0,25,27],[26,0,26,27],[27,0,27,27],[28,0,28,27],[29,0,29,27],[30,0,30,27]],"flags":["formulas_cached_only"]}
["财政衔接推进乡村振兴补助资金（巩固拓展脱贫攻坚成果和乡村振兴任务）项目清单"]
[]
["填报时间：  2025.1.13                填报人： 王玉莹                                                                                                                                                                  单位：万元、个 "]
["县（市、区）名称","序号","项目名称","是否出自项目库","建设地点",null,"项目类型（产业项目、基础设施、其他）","建设内容 ","建设规模",null,"资金规模（万元）",{"$nulls":3},"项目建设单位","项目建设单位负责人","项目前期准备情况","达到施工条件（是/否）","预计开工时间","预计竣工时间","使用方式","联农带农机制",{"$nulls":5},"绩效目标"]
[{"$nulls":4},"乡（镇）","村",null,null,"单位","数量",null,"使用资金类型（中央/省级）","衔接资金（万元）\n","资金指标文号",{"$nulls":7},"群众参与方式","受益对象",{"$nulls":3},"预期收益情况（万元）"]
[{"$nulls":22},"脱贫户",null,"非脱贫户"]
[{"$nulls":22},"户数","人数","户数","人数"]
["爱民区",1,"江西村高效养殖温室项目","是","三道关镇","江西村","产业项目","在江西村新建5栋高效养殖温室，占地面积6300平方米。","栋",5,300,"中央",162.06,"⿊财指（农）\n〔2025〕25号","三道关镇人民政府","潘鹏","预计4月1日前完成立项、选址、勘察设计等项目前期工作","否","2025.5.1","2025.11.1","资产租赁","收益分红",1,2,null,null,15,"增加村集体收入，每年分红15万"]
[{"$nulls":11},"省级",136.94,"⿊财指（农）\n〔2025〕26号"]
[{"$nulls":11},"区级",1]
["爱民区",2,"放牛村高效温室大棚项目","是","三道关镇","放牛村","产业项目","建设种植高效温室棚室3栋","个",3,125,"中央",82.4,"⿊财指（农）\n〔2025〕25号","三道关镇人民政府","潘鹏","预计4月1日前完成立项、选址、勘察设计等项目前期工作","否","2025.5.1","2025.11.1","资产租赁","收益分红",null,null,1,3,6.25,"增加村集体收入，每年分红6.25万"]
[{"$nulls":11},"结余",41.597637]
[{"$nulls":11},"区级",1.002363]
["爱民区",3,"丰收村村内丰收河桥梁建设项目","是","三道关镇","丰收村","基础设施","对原有危桥进行拆除，新建混凝土浇筑桥梁一座。","座",1,121,"中央",106,"⿊财指（农）\n〔2025〕25号","三道关镇人民政府","潘鹏","预计4月1日前完成立项、选址、勘察设计等项目前期工作","否","2025.5.1","2025.11.1",{"$nulls":7},"惠民农户960人出行"]
[{"$nulls":11},"省级",14,"⿊财指（农）\n〔2025〕26号"]
[{"$nulls":11},"区级",1]
["爱民区",4,"银龙村村内道路硬化及边沟建设项目","是","三道关镇","银龙村","基础设施","道路硬化1.6公里及新建排水边沟1公里","个",1,171.5,"省级",170.97,"⿊财指（农）\n〔2025〕26号","三道关镇人民政府","潘鹏","预计4月1日前完成立项、选址、勘察设计等项目前期工作","否","2025.5.1","2025.11.1",{"$nulls":7},"惠民银龙村450人出行"]
[{"$nulls":11},"区级",0.53]
["爱民区",5,"项目管理费","是","三道关镇",null,"其他",{"$nulls":3},13.530000000000001,"中央",3.54,"⿊财指（农）\n〔2025〕25号","三道关镇人民政府","潘鹏"]
[{"$nulls":11},"省级",9.99,"⿊财指（农）\n〔2025〕26号"]
["爱民区",6,"雨露计划","是","三道关镇",null,"其他","2025年“雨露计划”",null,null,0.6,"省级",0.6,"⿊财指（农）\n〔2025〕26号","三道关镇人民政府","潘鹏",{"$nulls":11},"解决2人教育问题"]
["爱民区",7,"小额信贷利息补贴","是","三道关镇",null,"产业项目","2025年脱贫人口（监测人口）小额信贷利息补贴",null,null,0.5,"省级",0.5,"⿊财指（农）\n〔2025〕26号","三道关镇人民政府","潘鹏",{"$nulls":11},"解决6户脱贫户产业增收"]
[{"$nulls":10},732.13,null,732.13]
["注：1.如同一项目使用了中央、省级衔接资金，该项目填两行，区分出中央省级衔接资金使用额度。"]
["2.按照国家绩效考核口径产业项目包括：种植养殖加工服务、休闲农业与乡村旅游、光伏项目、生态扶贫项目、扶贫小额信贷贴息、扶贫龙头企业合作社等经营主体贷款贴息。（产业项目的配套设施不算产业项目，如产业路、小型农田水利设施等）。"]
["3.项目前期准备情况为简述该项目立项、选址、土地预审、环评、工程勘察设计、工程招投标等项目前期工作准备情况。"]
["4.项目预计开、竣工时间按照全国防返贫信息监测系统标准，具体到“日”。"]
["5.使用方式：产业项目分为租赁、村集体自营，基础设施、其他项目不填。"]
["6.群众参与方式：务工增收、无劳分红。"]
["7.绩效目标按照全国防返贫信息监测系统项目绩效目标填写。"]
["8.同一项目多个实施地点的，全部拆分填写。"]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}